## For Aug-Sept 2018
[LOGO] [COMPANY NAME]
Sample Six-Month Enterprise Business Renewal Pre-Planning For [Renewal Effective Date]
| [Month 1] | [Month 2] | [Month 3] | [Month 4] | [Month 5] | [Month 6]
TEAM ACTION ITEMS
Conduct employee survey for feedback on current comprehensive benefits package
Prepare company finances and employee demographics and review for significant changes
Meet with benefits team to discuss survey findings and company needs
Communicate directives to benefits team: What are the company's goals this year?
Benefits team bird-dogs all group benefits policy renewals
Benefits team reviews policy renewals and prepares analysis and recommendations
Meet with benefits team to review analysis, market trends and opportunities
Internal discussions regarding options - queries/back-and-forth with benefits team
Benefits team works with vendors regarding any proposal modifications/rate negotiations
Final plan decisions due [ideally 6-8 weeks prior to renewal]
Build out company portal with renewal plans & rates [if have HRIS]
Set dates for employee meeting and/or employee 1:1 essions with benefits advisor(s)
Open enrollment notice to employees [no less than one month out]
Complete employee 1:1 advisory schedule
Federal Holiday
Employee group benefits education meeting and/or 1:1 remote essions take place
Team reschedules missed 1:1 sessions [if conducting team-assisted enrollment]
Completed forms, enrollment summaries & new deductions sent to client
[Administrator/HR] makes new enrollments/changes in online benefits portals
Update pay deductions for first (renewal month] pay run
Employees receive ID cards at their homes/new benefits begin [renewal date here]
Submit pay deduction changes to payroll for first renewal month pay run
Plan process debrief session in [renewal month]
TEAM RESPONSIBLITY LEGEND:
Group Administrator
Agent/Broker/Consultant
Company Employee Involvement
Vendors/Insurance Carriers |  |  |  | Karen M. Hsu
Enrollment Team{Agent/Benefits Advisors] |  |  |  | My Benefits Coach International
Holiday [Indicate, as will affect timeline] |  |  |  | CA Lic. 0B63037